## Final Quote
Source Row | BOM Name | BOM Unit ID | BOM Specifications/Size | BOM Quantity | BOM Reasoning | Quoted Part Number | Supplier | Supplier Qualification (ISO 9001) | Unit Price | Extended Price | Lead Time (days) | Estimated Ship Date | Quote Validity | Status | Status Detail | Evaluation Record Reference
4 | Servo motor bracket | RS-2210-B | Aluminum, 6061-T6 | 4 |  | 1234K56 | McMaster-Carr | Unknown | [5 empty] | SUBSTITUTION | Quote is for an equivalent part, not an exact match to the BOM line - needs engineering sign-off. Price not yet received. | comparison_bom.xlsx, Source Row 4
5 | Hex socket cap screw | 8420-K | M4 x 12mm | 16 |  | 8420-K | FastenCo | N/A (pre-approved) | [5 empty] | SUBSTITUTION | Quote is for an equivalent part, not an exact match to the BOM line - needs engineering sign-off. Price not yet received. | comparison_bom.xlsx, Source Row 5
6 | Right angle gearbox, 20:1 ratio |  | 20:1 | 2 | no mfg PN provided by client, matched from description | am-3103a | AndyMark | Unknown | [5 empty] | SUBSTITUTION | Quote is for an equivalent part, not an exact match to the BOM line - needs engineering sign-off. Price not yet received. | comparison_bom.xlsx, Source Row 6
7 | Terminal block | TB-100 | 10 position, 300V | 3 |  | TB-100 | ElectroConn | Unknown | [5 empty] | SUBSTITUTION | Quote is for an equivalent part, not an exact match to the BOM line - needs engineering sign-off. Price not yet received. | comparison_bom.xlsx, Source Row 7
8 | Linear bearing | LM-6UU | 6mm bore | 8 | qty looks high for a single-arm design, double-check | LM6UU | LinearMotion Inc | N/A (pre-approved) | [5 empty] | SUBSTITUTION | Quote is for an equivalent part, not an exact match to the BOM line - needs engineering sign-off. Price not yet received. | comparison_bom.xlsx, Source Row 8
9 | Power supply | PSU-24-5A | 24V 5A | 1 |  | PSU-24-5A | MeanTech | Unknown | [5 empty] | SUBSTITUTION | Quote is for an equivalent part, not an exact match to the BOM line - needs engineering sign-off. Price not yet received. | comparison_bom.xlsx, Source Row 9
10 | Custom laser-cut acrylic enclosure panel |  | 3mm thickness | 2 | one-off custom part for this design, no standard catalog match expected | [8 empty] | UNSOURCED | No supplier could be identified for this line. | comparison_bom.xlsx, Source Row 10

## Review Needed
Source Row | Issue
6 | Has reasoning/notes text but consistency check could not run (no LLM access) - needs manual read-through.
8 | Has reasoning/notes text but consistency check could not run (no LLM access) - needs manual read-through.
10 | Has reasoning/notes text but consistency check could not run (no LLM access) - needs manual read-through.
4 | Matched by description only, no manufacturer part number was available/verifiable - needs engineering sign-off before treating as equivalent.
5 | Unit ID found in catalog, but plausibility could not be confirmed (no LLM access) - verify this is the right part before treating it as exact.
6 | Matched by description only, no manufacturer part number was available/verifiable - needs engineering sign-off before treating as equivalent.
7 | Unit ID found in catalog, but plausibility could not be confirmed (no LLM access) - verify this is the right part before treating it as exact.
8 | Unit ID found in catalog, but plausibility could not be confirmed (no LLM access) - verify this is the right part before treating it as exact.
9 | Unit ID found in catalog, but plausibility could not be confirmed (no LLM access) - verify this is the right part before treating it as exact.
10 | No exact or probable match found - route to supplier discovery from scratch.
4 | 'McMaster-Carr' is not yet an approved vendor (ISO 9001 status: Unknown) - needs qualification review before an RFQ can be sent.
6 | 'AndyMark' is not yet an approved vendor (ISO 9001 status: Unknown) - needs qualification review before an RFQ can be sent.
7 | 'ElectroConn' is not yet an approved vendor (ISO 9001 status: Unknown) - needs qualification review before an RFQ can be sent.
7 | 'ElectroConn' has no contact/channel on file - cannot send an RFQ until this is captured during qualification.
9 | 'MeanTech' is not yet an approved vendor (ISO 9001 status: Unknown) - needs qualification review before an RFQ can be sent.
9 | 'MeanTech' has no contact/channel on file - cannot send an RFQ until this is captured during qualification.
10 | No supplier candidates found - needs manual sourcing, no automated path available yet.
4 | RFQ to 'McMaster-Carr' drafted but not sent (no SMTP access).
5 | RFQ to 'FastenCo' drafted but not sent (no SMTP access).
6 | RFQ to 'AndyMark' drafted but not sent (no SMTP access).
7 | Distributor part - pricing should come from a Stage 2 catalog query, not an RFQ. Skipped here.
9 | Distributor part - pricing should come from a Stage 2 catalog query, not an RFQ. Skipped here.
4 | Email content received for RESIN8-RFQ-0004 but quote fields could not be extracted (no LLM access) - needs manual read: Thanks for reaching out. For part 1234K56 (Aluminum mounting bracket for NEMA 17 servo motors), qty 4: unit price $8.75, extended price $35.00. In stock, ships in 2 business days. Quote valid 30 days
6 | Email content received for RESIN8-RFQ-0006 but quote fields could not be extracted (no LLM access) - needs manual read: We can supply the am-3103a gearbox. Note: minimum order quantity is 5 units, your request was for 2 - happy to quote at 5 if that works. Unit price at MOQ $42.00, extended $210.00. Lead time 3 weeks,
8 | Portal content received for 8 but quote fields could not be extracted (no LLM access) - needs manual read: My Account > Quotes Quote #Q-88213 - LM6UU Linear ball bearing, 6mm bore Quantity: 8 Unit price: $3.10 Extended: $24.80 Availability: In stock Ships: same day if ordered before 2pm This quote i
4 | Only one candidate quote available for this line - nothing to compare against yet (see Stage 2/3 known limitation).
6 | Only one candidate quote available for this line - nothing to compare against yet (see Stage 2/3 known limitation).
8 | Only one candidate quote available for this line - nothing to compare against yet (see Stage 2/3 known limitation).